## Slide 1
■ DOSTO NEU
01 / 11
PROJECT STATUS &
INTERDEPENDENCY
REVIEW
Nomad / ÖBB / Stadler
ABBAS RIZVI — NOMAD
01.07.2026

## Slide 2
■ DOSTO NEU
02 / 11
PURPOSE OF TODAY
Align on status, technical risks, and the process to close open items — together, on the record.
AGENDA — PART 1
1. Current project status
2. CCU stability — single traction
3. Multi-traction roadmap
AGENDA — PART 2
4. Release & change management process
5. Remote SW updates & notification process
6. Vehicle config transparency / SW-version visibility
7. Schedule, quality & warranty impact
8. Agreement on next steps
DOSTO NEU — INTERDEPENDENCY REVIEW
02 / 11

## Slide 3
■ DOSTO NEU
03 / 11
WHAT'S ACTUALLY BLOCKING WHAT
Today's agenda items, mapped against their real dependency
Agenda item | Design Freeze | Functionality Testing | No VO / Out of Scope | Nomad-Actionable Now
CCU stability — single traction | — | — | — | ✓
Multi-traction roadmap | — | — | ● | ✓
Release & change management process | ● | ● | — | —
Remote SW updates & notification process | ● | ● | — | —
Vehicle config transparency / SW visibility | — | — | — | ✓
● = blocking dependency ● = commercial-process dependency ✓ = Nomad already delivering
Three of five items trace back to two things ÖBB control: design freeze and functionality testing. Nomad's own Q2 2026 phase plan shows engineering time fully committed to tracked, dated work — and contains zero line items for the multi-traction remediation already delivered. That work was unplanned and unbudgeted.
DOSTO NEU — INTERDEPENDENCY REVIEW
03 / 11

## Slide 4
■ DOSTO NEU
04 / 11
DELIVERY STATUS VS. COMMITTED PLAN
Source: DostoNeu Phase Plan Q2 2026 — status as of 01 July 2026
NOMAD-OWNED — ACTIVE RIGHT NOW
NMS Rollout active KW19–24 | In Progress
Portal: fleet rollout active KW22–30 | In Progress
Portal: backend check active KW24–28 | In Progress
Release notes — sign-off active KW19–26 | In Progress
Fleet migration to MAR5 EMEAE-5395, at-risk KW25 | In Progress
Switch v9 for fleet TRIAG-8521 | To Do
VDS Firmware 7.4.8 HWI-257 | To Do
ÖBB / STADLER-OWNED — BLOCKING
Design freeze (Application layer) due 16 Jun — 15 days overdue | Overdue
Freigabe ÖBB — PM-06 Functional Test Report | To Do
Freigabe ÖBB — PM-07 Ready-for-Service | To Do
Freigabe ÖBB — PM-08 Kapazitätsplan blocks PM-12 fleet acceptance | To Do
Freigabe Phase 4 owner: Stadler — confirm portal done | To Do
Final Nomad technical description — review security & Stadler | In Progress
Not on this plan at all: the multi-traction / v9 remediation (RSTP fix, native-VLAN containment) — delivered in goodwill, fully unbudgeted, on top of the schedule above.
DOSTO NEU — INTERDEPENDENCY REVIEW
04 / 11

## Slide 5
■ DOSTO NEU
05 / 11
CCU STABILITY — SINGLE TRACTION
FINDING 1 — MODEM / SIM INSTABILITY
Root cause: CPDL hardware fault on modem carrier blades — first two SIM slots fail to come up, reducing redundant dual-SIM operation to a single SIM. Fix: blade replacement. 4 trains completed to date (2 by SPL, 2 by Nomad); remaining fleet count and completion target [ Abbas: to confirm ].
FINDING 2 — POWER RESETS (IGNITION-SENSE SIGNATURE)
Repeatable signature captured via hardened CCU logging on 4736-110: ignition-sense voltage drops to 0V while main input voltage stays stable; ignition reads 0 for ~90s, then the CCU hard-cuts. Three occurrences captured, 16–18 June 2026. Status: root cause narrowed to the ignition-sense input, not the power supply. Investigation ongoing — not yet resolved.
Other items raised in ÖBB's 10 March test protocol (client isolation on staff WLAN, switch-visibility during the incident) remain open pending design freeze and functionality testing completion — see slide 10.
DOSTO NEU — INTERDEPENDENCY REVIEW
05 / 11

## Slide 6
■ DOSTO NEU
06 / 11
MULTI-TRACTION ROADMAP
✓ FOUND AND FIXED, FAST — NOMAD-OWNED
12 June coupling test surfaced a perpetual ~2s RSTP topology-change storm on coupled 6+6 consists. Root cause: asymmetric coupler port-costs in Nomad's own v8 template. Fixed in v9 (symmetric cost 20000, max-age raised to 38, native-VLAN containment) — validated stable across all 2-train orientations by the 30 June re-test.
✓ CCTV / ZFR DEGRADATION — RESOLVED, SAME FIX
The 30 June test isolated the variable: the v9 cost fix alone — no firewall change, no VLAN-5 change — stopped the churn and the CCTV feed recovered immediately. This revises the earlier hypothesis: the degradation was driven by the RSTP storm flooding camera traffic, not by any Stadler firewall interaction. No further Stadler dependency on this item.
Roadmap input: triple traction (3×6, 54 switches) exceeds RSTP's node/diameter limits — requires an L3 / routed segmentation redesign if triple traction is ever required. Flagged now, not a current defect.
This work was delivered as goodwill, outside contracted scope, and is not on Nomad's committed phase plan — see Scope & VO Status, slide 9.
DOSTO NEU — INTERDEPENDENCY REVIEW
06 / 11

## Slide 7
■ DOSTO NEU
07 / 11
CHANGE & UPDATE PROCESS — READY FOR O&M
RELEASE & CHANGE MANAGEMENT
A formal process — release notes, impact assessment, sign-off gates — is already defined for the O&M phase.
REMOTE UPDATES & NOTIFICATION
Update trigger, advance notification, and post-update verification are already defined for the O&M phase.
BOTH ARE BLOCKED FROM ACTIVATING
The fleet cannot enter O&M until design freeze and functionality testing (bench + prototype) are complete. These are not missing Nomad capabilities — they are ready and waiting on the same two ÖBB/Stadler-owned gates. See slide 3.
The phase plan itself has no target date for O&M handover — the ÖBB-owned "decision on maintenance" line item has no stated deadline.
DOSTO NEU — INTERDEPENDENCY REVIEW
07 / 11

## Slide 8
■ DOSTO NEU
08 / 11
VEHICLE CONFIG TRANSPARENCY & SW VISIBILITY
ÖBB has requested Stadler be given access to view switch config & firmware version. Two candidate routes — only one is safe to hand to a third party:
✗ ENGINEERING PAGES — NOT VIABLE FOR STADLER
Now carries a live "obn update" control that triggers a fleet-wide device update. This cannot be exposed to a third party — no way to grant read-only access without also granting that trigger.
✓ NMS — THE CORRECT ROUTE
Already exposes, per train: exact switch config & firmware version, and real-time port-level alerts (e.g. port-down). Read-only, no destructive control surface. Live today.
Ask: Stadler access to be provisioned via NMS, not Engineering Pages. If NMS is missing something Stadler specifically needs, please specify it.
DOSTO NEU — INTERDEPENDENCY REVIEW
08 / 11

## Slide 9
■ DOSTO NEU
09 / 11
SCOPE & VARIATION ORDERS
Nomad has already delivered significant work beyond Chapter 6 standard/extended scope, at no charge, in goodwill:
IP planning for 267 Stadler 3rd-party devices per train
Repeated switch-config re-issues from incomplete Stadler design freeze
Portal-Lite pages built post-CMS handover to ÖBB
Fleet-wide L2 diagnostics & cabling fault register
Multi-traction network-fabric remediation (v9/v10)
Formally communicated to ÖBB in writing — Chapter 6, ND-BID-OBB-036 Technical Description v0.3.
NO VO HAS EVER BEEN QUOTED FOR THIS SPECIFIC WORK
The multi-traction network-fabric work (common network across coupled consists, shared switch-config management) is not just unordered — it has never appeared in any Nomad offer, including the lapsed Extended offer (EXT1, valid to 01.03.2024). Nomad's Q2 2026 phase plan confirms it: zero line items budgeted for this work — it was delivered entirely outside the committed, resourced schedule.
Ask: no further work outside Chapter 6 standard scope — multi-traction or otherwise — proceeds without an approved RFQ/VO, using the provided template.
Live example of the same pattern: ÖBB's own Application-layer design freeze — due 16 June 2026, still open as of 01 July 2026.
DOSTO NEU — INTERDEPENDENCY REVIEW
09 / 11

## Slide 10
■ DOSTO NEU
10 / 11
SCHEDULE, QUALITY & WARRANTY IMPACT
Trains are entering ÖBB commercial service without a completed design freeze, and without completed functionality testing on bench and prototype train.
MAIN ITEM TO ADDRESS — DEVICES-NOT-FOUND REGISTER
150
not-answering devices
live-verified, across 35 trains
(91 on 6-car · 59 on 4-car)
REGISTER v1.1 · 01 JUL 2026
Fleet-wide list of end-devices not answering on the onboard network — displays, intercoms (Sprechstelle), energy meters. On every listed port the switch port is up, transmitting, with zero RX frames and zero CRC / carrier / error counters: the L2 fabric is healthy and the device on the far side is absent or silent. These are Stadler-side device / fitment items, not Nomad network faults — and they need a fleet-wide plan to clear.
Note: excludes two offline 4-car trains (4734-101, 4734-190) pending live re-verification. Plus 12 cabling / hardware faults fleet-wide (7 still open).
This risk stems from process and schedule decisions — not Nomad equipment defects. Flagging now, before warranty exposure grows.
DOSTO NEU — INTERDEPENDENCY REVIEW
10 / 11

## Slide 11
■ DOSTO NEU
11 / 11
PROPOSED NEXT STEPS
1
ÖBB: COMPLETE DESIGN FREEZE
Application-layer design freeze — no further slip beyond the 16 June milestone.
2
ÖBB: SUBMIT RFQs
Against Chapter 6, using the provided template, for any additional/changed scope — before further requests are actioned.
3
ÖBB: NO OUT-OF-SCOPE WORK WITHOUT A VO
Applies to multi-traction and any other request outside Chapter 6 standard scope. Nomad to re-share the RFQ template.
4
JOINT: FORMAL CHANGE PROCESS
Agreement on release & change management process. [ target date ]
DOSTO NEU — INTERDEPENDENCY REVIEW
11 / 11