## Status
DOSTO Project — Master Status Tracker
Single source of truth across all workstreams. Filter/sort by Workstream or Status. Update the row + Last updated when state changes.
Generated 2026-06-20 (replaces PROJECT-STATUS.md). Per-train detail still lives in fleet-status.md; cabling detail in cable-issues-register.md.
Workstream | Item | Owner | Status | Detail | Last updated
Commissioning | v8 rollout — fleet (per-train detail in fleet-status.md) | Nomad | In progress | 4736: 11 done, 4 paused, 1 error (118 PoE), 7 unknown. 4734: 8 done, 6 paused, 1 blocked. 4706/4705: mostly unknown. | 2026-06-20
Commissioning | 4736-114 / Fzg 142 — misimage corrected | Nomad | In progress | RESOLVED misimage (was imaged as 4706-103/T17). Now box1-t27 @ 10.179.27.1, 18/18 sw v8-142, 24/24 AP, vlan7 .199.2/17 carrying traffic, Zabbix 6027 healthy. Remaining: AP fw push 0/24 -> 6.11.2-0. | 2026-06-20
Commissioning | AP firmware partition-swap wall | Nomad/R&D | Todo | Many staged-not-activated APs across fleet; obn update f stages fw but reboot doesn't activate. Bug11 now reports honestly; per-AP retry + LuCI bypass. R&D candidate. | 2026-06-20
Commissioning | 4705 platform unsupported by commission skill | Nomad | Blocked | dosto-commission-train only enumerates 4-car/6-car; fv5-* (4705) needs skill update before commissioning. | 2026-05-22
Commissioning | OBN persisted-baseline drift (top-up bug10/11) | Nomad | Todo | Rows claiming 8/8 or 9/9 are silently <=9/11 or <=10/11. 14 pre-bug10 + 6 pre-bug11 trains need top-up. Low urgency. | 2026-06-09
SDD | SDD-002 T1 — QoS/DSCP per-VLAN write-back | Nomad | Todo | Produces v2.4. The one item closable with no external input. | 2026-06-19
SDD | SDD-003 — 15 mechanical comments | Nomad | Done | All 15 done in v3-tracked. | 2026-06-19
SDD | SDD-003 — 10 comments blocked on inputs (T2-T11) | Nomad/OEBB | Blocked | Dimensioning sheet (biggest unblocker), NAT ratio, Wi-Fi channel plan, VLAN47, Project-ID confirm, diagrams, portal screenshots/spec/naming, NTP source. | 2026-06-19
SDD | SDD-003 #154 — commercial dispute | Other | Deferred | Handled separately by email. | 2026-06-19
Cabling/HW | Reg #1 — 4734-101 E2<->B1 wrong neighbour | Stadler | Blocked | OPEN — re-patch E<->B trunk. | 2026-05-22
Cabling/HW | Reg #4 — 4736-109 B3 e0-4 AP not connected | Stadler | Blocked | OPEN. | 2026-06-09
Cabling/HW | Reg #5 — 4736-104 D3 e1-2 physical-layer | Stadler | Blocked | OPEN — data pairs dead, cable replace. | 2026-05-22
Cabling/HW | Reg #7 — 4736-108 A2<->A3 e0-1 physical-layer | Stadler | Blocked | OPEN — RX errors under load; SFP/cable. Caused storm. | 2026-05-29
Cabling/HW | Reg #8 — 4736-115 B3 e0-4 Coach6 AP not connected | Stadler | Blocked | OPEN. | 2026-06-09
Cabling/HW | Reg #9 — 4736-118 E1 PoE PSE fault | Stadler | Blocked | OPEN — degraded KMkon module, whole-switch PoE dead; replace. | 2026-06-15
Cabling/HW | Reg #11 — 4736-114 14x FIS display/energy-meter ports | OEBB/Stadler | Blocked | OPEN — 14 e2-* display/meter ports link-down. CCU-side EXHAUSTED (port details, 40 up siblings, bounce x14, logs clean). Verification requested via OEBB report 2026-06-20. May be fit-out state not faults. | 2026-06-20
OBN bugs | 11-bug suite characterised + dosto-obn-patches | Nomad | Done | Bugs 1-10 code + bug11 AP-fw verify; applied/verified by skill. | 2026-06-09
OBN bugs | nd-obn 2.2.23 native fixes understood | Nomad | Done | 2.2.23 ships bugs 1-10 native; only bug11 hand-patch; never run fix_obn.py on it. | 2026-06-10
OBN bugs | TRIAG-8585 — upstream R&D ticket | R&D | In progress | Tracks 11 code + 1 infra bug for v8 hand-patches. | 2026-06-09
OBN bugs | TFTP conntrack helper — Puppet fix | R&D | Blocked | Runtime modprobe+iptables works but wiped on reboot; needs Puppet in 60-allow-management. | 2026-06-09
OBN bugs | dosto-ap-firmware-update skill precheck bugs | Nomad | Todo | snmpget too strict; journalctl ISO date. | 2026-06-09
OBN bugs | MAR5 hostname equivalents from R&D | R&D | Todo | Awaiting R&D. | 2026-06-09
Zabbix/NMS | SNMP cred model resolved | Nomad | Done | SW user=snmpadmin, AP user=admin, both NomadStayOut!. | 2026-06-08
Zabbix/NMS | NV6 template AP-user fix (v9) | Nomad | Done | securityName snmpadmin->admin. NV4/FV5/bench unchecked. | 2026-06-08
Zabbix/NMS | Switch template wrong OIDs corrected | Nomad | Done | port-status + firmware OIDs fixed. | 2026-06-08
Zabbix/NMS | NMS CDC page empty (Alpin) — stale OVH creds | Nomad/sysops | Blocked | PARKED until Mon 2026-06-22 on sysops creds; then fix both projects. | 2026-06-20
Zabbix/NMS | Proxy CacheSize/LLD bloat | Nomad | In progress | ifDescr over-discovery OOM; {#IFDESCR} filter added, CacheSize=128M stopgap. | 2026-06-09
Zabbix/NMS | Stale-template-IP reconciliation | Nomad | In progress | Reconcile SNMP-dead host IPs from OBN discovery. | 2026-06-09
6040/GPS | 6040 GPS blank in NMS — rtl_project_id 51 not 50 | Nomad | Blocked | Publish namespace stuck p51; OEBB NMS monitors p50. Fix in facter/telemetry/bridge. | 2026-06-15
6040/GPS | 6040 link-info gap | Nomad | Done | Was post-reboot modem reidentify transient; self-healed. | 2026-06-15
6040/GPS | GPS MQTT bridge 'mismatch' — RETRACTED | Nomad | Done | Bridge is correct; gap is NMS-side. Do not touch bridge. | 2026-06-15
Investigations | Fzg 19/20 B&E WAP swap | Nomad | In progress | Customer-reported WE1/WE2 swap; ruled out OBN/cabling/config; suspect SSID config or coach orientation. | 2026-06-15
Investigations | Fzg 1 partial health check | Nomad | In progress | Partial L2 sweep box1-t4; CCU no sshpass, RO rootfs; 2 APs missing; train offline mid-sweep. | 2026-06-15
Investigations | Fzg136 obn user-count slow-SNMP | Nomad | Done | Slow but completes every cycle; not stuck, no action. | 2026-06-15
Tooling | Auto-scanner | Nomad | In progress | Tier-1 reachability stub built+tested; Tier-2 + bootstrap deferred. | 2026-06-09
Tooling | Orchestration stack | Nomad | Done | Inline /dosto-orchestrate + worker + 19-stage commission-train + 4 contracts. Feature-complete. | 2026-06-09
Tooling | Jira integration decision | Nomad/team | Blocked | Surveyed EMEAE; 3 options. Blocked on team coordination (Kemeter/Behnam/Zejnelovic). | 2026-05-10

## Summary
Status summary
Status | Count | Workstream | Count
Done | 10 | Commissioning | 5
In progress | 8 | SDD | 4
Todo | 5 | Cabling/HW | 7
Blocked | 13 | OBN bugs | 6
Deferred | 1 | Zabbix/NMS | 6
Total | 37 | 6040/GPS | 3
|  | Investigations | 3
|  | Tooling | 3