## Slide 1
■ DOSTO NEU
01 / 09
PROJECT STATUS &
INTERDEPENDENCY
REVIEW
Nomad / ÖBB / Stadler
ABBAS RIZVI — NOMAD
01.07.2026

## Slide 2
■ DOSTO NEU
02 / 09
PURPOSE OF TODAY
Align on status, technical risks, and the process to close open items — together, on the record.
AGENDA — PART 1
1. Current project status
2. CCU stability — single traction
3. Multi-traction roadmap
AGENDA — PART 2
4. Release & change management process
5. Remote SW updates & notification process
6. Vehicle config transparency / SW-version visibility
7. Schedule, quality & warranty impact
8. Agreement on next steps
DOSTO NEU — INTERDEPENDENCY REVIEW
02 / 09

## Slide 3
■ DOSTO NEU
03 / 09
Current project status
Source: DostoNeu Phase Plan Q2 2026 — status as of 01 July 2026
NOMAD-OWNED
NMS Rollout active KW19–24 | In Progress
Portal: fleet rollout active KW22–30 | In Progress
Portal: backend check active KW24–28 | In Progress
Release notes — sign-off active KW19–26 | In Progress
Fleet migration to MAR5 EMEAE-5395, at-risk KW25 | In Progress
Switch v9 for fleet TRIAG-8521 | To Do
VDS Firmware 7.4.8 HWI-257 | To Do
ÖBB / STADLER-OWNED
Design freeze (Application layer) due 16 Jun — 15 days overdue | To Do
Freigabe ÖBB — PM-06 Functional Test Report | To Do
Freigabe ÖBB — PM-07 Ready-for-Service | To Do
Freigabe ÖBB — PM-08 Kapazitätsplan blocks PM-12 fleet acceptance | To Do
Freigabe Phase 4 owner: Stadler — confirm portal done | To Do
Final Nomad technical description — review security & Stadler | In Progress
Not on this plan at all: the multi-traction / v9 remediation (RSTP fix, native-VLAN containment)
DOSTO NEU — INTERDEPENDENCY REVIEW
03 / 09
Context: Commissioning done a long time ago. Normalizing fleet and aligning configuration

## Slide 4
■ DOSTO NEU
04 / 09
CCU STABILITY — SINGLE TRACTION
FINDING 1 — MODEM / SIM INSTABILITY
Root cause: CPDL hardware fault on modem carrier blades – HW Replacement ongoing Root cause: SIMs stay in “Registered” status after reboot – Watcher script implement to reboot modem + Permenant fix in NC 2026.2 release.
FINDING 2 — POWER RESETS (IGNITION-SENSE SIGNATURE)
Repeatable signature captured via hardened CCU logging on 4736-110: ignition-sense voltage drops to 0V while main input voltage stays stable; ignition reads 0 for ~90s, then the CCU hard-cuts. Three occurrences captured, 16–18 June 2026. Status: root cause narrowed to the ignition-sense input, not the power supply. Investigation ongoing — not yet resolved.
Other items raised in ÖBB's 10 March test protocol (client isolation on staff WLAN, switch-visibility during the incident) remain open pending design freeze and functionality testing completion.
DOSTO NEU — INTERDEPENDENCY REVIEW
04 / 09

## Slide 5
■ DOSTO NEU
05 / 09
MULTI-TRACTION ROADMAP
DESIGN REVIEW — NOMAD + VDSRAIL + ÖBB
12 June coupling test surfaced a perpetual ~2s RSTP topology-change storm on coupled 6+6 consists. Root cause: asymmetric coupler port-costs in Nomad's own v8 template. Fixed in v9 (symmetric cost 20000, max-age raised to 38, native-VLAN containment) — However this does not provide deterministic port blocking on the front coupler ports.
✓ CCTV / ZFR DEGRADATION — Caused by ASYMMETRIC Routing – Disable one coupler port until Design Review is complete
The 30 June test isolated the variable: the v9 cost fix alone — no firewall change, no VLAN-5 change — stopped the churn and the CCTV feed recovered immediately. This revises the earlier hypothesis: the degradation was driven by the RSTP storm flooding camera traffic, not by any Stadler firewall interaction. No further Stadler dependency on this item.
Roadmap input: triple traction (3×6, 54 switches) exceeds RSTP's node/diameter limits — requires an L3 / routed segmentation redesign if triple traction is required.
Scope out of contract. Awaiting IFQ for next steps.
DOSTO NEU — INTERDEPENDENCY REVIEW
05 / 09

## Slide 6
■ DOSTO NEU
06 / 09
Release & change management process
In delivery
    Missing design freeze for a very long time
    Target was to normalise to prepare service only
    Today, we have a release note mentioning V8 on switches
    This is deployed on-board
    Changes mentioned in RN, approved by ÖBB
O&M
A formal process — release notes, impact assessment, sign-off gates — is already defined for the O&M phase:
Update trigger, advance notification, and post-update verification
BOTH ARE BLOCKED FROM ACTIVATING
The fleet cannot enter O&M until design freeze and functionality testing (bench + prototype) are complete.
DOSTO NEU — INTERDEPENDENCY REVIEW
06 / 09

## Slide 7
■ DOSTO NEU
07 / 09
Remote software updates and notification process
Vehicle configuration transparency and SW-Version visibility
Train status today
  All trains (4 & 6 coaches) are updated after communication with ÖBB
  New trains are commissioned with this version
  Trains 4705 (3 trains) & 4706 (3) update has started and will be completed as trains come online.
NMS exposes, per train:
  Switch configuration & firmware version
  Real-time port-level alerts (e.g. port-down)
  AP configuration & firmware version
DOSTO NEU — INTERDEPENDENCY REVIEW
07 / 09

## Slide 8
■ DOSTO NEU
08 / 09
SCHEDULE, QUALITY & WARRANTY IMPACT
  No specific warranty topic
  Warranty for material starts when delivered
  O&M contract then
  Upgrade can be done in usual O&M process if needed
DOSTO NEU — INTERDEPENDENCY REVIEW
08 / 09

## Slide 9
■ DOSTO NEU
09 / 09
Agreement on next steps
Agenda item | Design Freeze | Functionality Testing | No VO / Out of Scope | Nomad-Actionable Now
CCU stability — single traction | — | — | — | ✓
Multi-traction roadmap | — | — | ● | ✓
Release & change management process | ● | ● | — | —
Remote SW updates & notification process | ● | ● | — | —
Vehicle config transparency / SW visibility | — | — | — | ✓
● = blocking dependency ● = commercial-process dependency ✓ = Nomad already delivering
Design freeze and functionality testing expected from ÖBB
IFQ needed to analyze multi-traction GAP
Analysis provided on current status for external components
DOSTO NEU — INTERDEPENDENCY REVIEW
09 / 09