## Summary
| Issued To: | Nomad Only
Nomad Reference No.:
| Issue: | 1
| Date: | 2026-02-11
| Prepared by: | Giovanni Di Maio
| Technical Contact: | Giovanni Di Maio
| Approved By: | Derek Abdinor
Project Name:
SUMMARY
NOTES
V1 - Initial version.

## DANI
OBB: DANI
PE | Commissioning Date | Status | Commissioning Report | Train Number | Fzg ID | CCU S/N | Project ID | Train NC ID | Environment | CCU Global IP | Config Branch | NC Release | Cabling Correct Orientation | Notes
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE

## ProjectName
OBB: ProjectName
PE | Commissioning Date | Status | Commissioning Report | Train Number | Fzg ID | CCU S/N | Project ID | Train NC ID | Environment | CCU Global IP | Config Branch | NC Release | Cabling Correct Orientation | Notes
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE
|  | To Do | [10 empty] | FALSE

## Dosto Neu
OBB: Dosto Neu
PE | Commissioning Date | Status | Train Number | Fzg ID | CCU S/N | Project ID | Train NC ID | Environment | CCU Global IP | mar3/mar5 | switch version | AP Firmware | OBN status | Config Branch | NC Release | Portal | Cabling Correct Orientation | Notes | STADLER ISSUES BY ACCEPTANCE (ANNAHME)
Davud | Wed 10.07.24 | Done | 4734-101 | 4734.101 | 2427110029 |  | T4 | CCU | 10.179.4.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 |  | FALSE | PRIO TYPETEST : Dont update without strict confirmation Stadler/OEBB | 08.05 - CABLE DEFEKT
Davud | Wed 10.07.24 | Done | 4736-101 | 4736.101 | 2427110015 |  | T7 |  | 10.179.7.1 | mar5 | v7 | 6.10.0 |  |  | 2025.2.1 |  | FALSE | Vehicle 4736101 continues to have issues with communication between the OBS and our firewall. The OBS IP address is not reachable. In addition, the ÖBB Wi‑Fi on the train is not working; it is not possible to connect (the login page does not appear). I also believe that the Wi‑Fi access points in the lower deck, WE1 and WE2, have an incorrect configuration, as the channels appear to be swapped. Furthermore, the access points seem to be using duplicate channels (for example, channel 44 and 44 at the same time).** | 01.05 - CCU NOT UPDATED BY CPLD. IMAGE UPDATED BY NOMAD
Davud | Wed 10.07.24 | replaced train | 4734-102 | 4734.102 | 2567110026 (sent to 4736 102) |  | T6 |  | 10.178.6.1 | mar3 | v2 | 6.10.0 |  |  | 2024 |  | FALSE | Train to be replaced by 4734 190 - number retired
Davud | Wed 10.07.24 | Done | 4734-103 | 4734.103 | 2427110020 |  | T5 | Stadler: this has configs from Fzg 5 on | 10.179.5.1 | mar5 | v7 | 6.10.0 |  |  | 2025.2.1 |  | FALSE
Davud | Wed 07.08.24 | Done | 4736-102 | 4736.102 | 2567110026 |  | T14 or T47_ |  | 10.179.47.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE | 08,05 : Cabling false
Davud | Wed 21.08.24 | Done | 4734-104 | 4734.104 | 2447110011 |  | T9 |  | 10.179.9.1 | mar5 | unknown | 6.10.0 |  |  | 2025.2.1 |  | FALSE | PRIO TYPETEST : Dont update without strict confirmation Stadler/OEBB
Davud | Wed 04.09.24 | Done | 4736-103 | 4736.103 | 2447110007 |  | T11 | landseite | 10.179.11.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 |  | FALSE
Davud | Wed 18.09.24 | Done | 4736-104 | 4736.104 | 2447110009 |  | T10 |  | 10.179.10.1 | mar5 | v8 | 6.11.2 |  |  | 2025.2.1 | OK | FALSE | Davud testing sensor gateways CCU keeps losing connection, cause unknown. must be tested with remote laptop 07.05 2 diff versions of AP config
Davud | Wed 02.10.24 | Done | 4736-105 | 4736.105 | 2427110031 |  | T1 |  | 10.179.1.1 | mar5 | v8 | 6.11.2 |  |  | 2025.2.1 | OK | FALSE
Davud | Wed 16.10.24 | Done | 4736-106 | 4736.106 | 2457110013 |  | T19 |  | 10.179.19.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE | During test drive CCU lost power after 20 minutes, not accessible via Cable or Internet. Restarted. R+D ticket (eurostar) need someone on train, (fan tray and carrier blades)
Davud | Wed 30.10.24 | Done | 4736-107 | 4736.107 | 2457110016 |  | T25 | CCU fixed - A1? | 10.179.25.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE | As at 13.04 no signal
Davud | Wed 13.11.24 | Done | 4736-108 | 4736.108 | 2447110006 |  | T8 |  | 10.179.8.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE | CCU migrated to mar5 and switch config updated to v7 on 17/02/2026.
Abbas | 23.01.2025 | Done | 4736-109 | 4736.109 | 2457110009 |  | T28 |  | 10.179.28.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE | This is a Prio vehicle to be used as a test train, pls confirm everything functioning
Davud | 12.03.2025 | Done | 4736-110 | 4736-110 | 2457110014 |  | T23 |  | 10.179.23.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE | CCU migrated to mar5 and switch config updated to v6 on 16/02/2026.+D17:Q17
Davud | 17.03.2025 | Done | 4736-111 | 4736.111 | 2457110002 |  | T24 |  | 10.179.24.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Davud | 18.04.2025 | Done | 4736-112 | 4736.112 | 2427110019 |  | T40 |  | 10.179.40.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Davud | 02.05.2025 | Done | 4736-113 | 4736.113 | 2457110003 |  | T22 |  | 10.179.22.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Davud | 16.05.2025 | Done | 4736-114 | 4736.114 | 2457110007 |  | T27 |  | 10.179.27.1 | mar5 | nomad | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Davud | 11.06.2025 | Done | 4736-115 | 4736.115 | 2457110012 |  | T18 |  | 10.179.18.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE | 2026-06-08: 18/18 SW reachable, nv6-*-v8-143, fw 7.4.2; AP fw push pending (Gate 4)
Davud | 03.07.2025 | Done | 4736-116 | 4736.116 | 2457110001 |  | T16 |  | 10.179.16.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Davud | 22.07.2025 | Done | 4736-117 | 4736.117 | 24A7110007 |  | T32 |  | 10.179.32.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Davud | 20.08.2025 | Done | 4736-118 | 4736.118 | 2457110010 |  | T21 |  | 10.179.21.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Davud | 29.08.2025 | Done | 4736-119 | 4736.119 | 2447110005 |  | T12 |  | 10.179.12.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Clemens | 19.09.2025 | Done | 4736-120 | 4736.120 | 2427110027 |  | T2 |  | 10.179.2.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Clemens | 03.10.2025 | Done | 4734-105 | 4734.105 | 24A7110011 |  | T30 |  | 10.179.30.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Clemens | 16.10.2025 | Done | 4734-106 | 4734.106 | 24A7110003 |  | T31 |  | 10.179.31.1 | mar5 | v8 | 6.10.0 | OK |  | 2025.2.1 | OK | FALSE
Clemens | 24.10.2025 | Done | 4734-107 | 4734.107 | 24A7110004 |  | T35 |  | 10.179.35.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Clemens | 08.11.2025 | Done | 4734-108 | 4734.108 | 24A7110009 |  | T29 |  | 10.179.29.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Clemens | 19.11.2025 | Done | 4734-109 | 4734.109 | 24A7110005 |  | T38 |  | 10.179.38.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Clemens | 02.12.2025 | Done | 4734-110 | 4734.110 | 24A7110006 |  | T36 | PREMIERFAHRT | 10.179.36.1 | mar5 | v6 | 6.10.0 |  |  | 2025.2.1 |  | FALSE
Clemens | 09.12.2025 | Done | 4734-111 | 4734.111 | 24A7110010 |  | T39 |  | 10.179.39.1 | mar5 | v8 | 6.11.2 |  |  | 2025.2.1 | OK | FALSE | switch config updated to v7 on 03/03/2026.
Johannes | 19.12.2025 | Done | 4734-112 | 4734.112 | 24A7110002 |  | T37 | SCHATTENFAHRT | 10.179.37.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE | switch config updated to v7 on 03/03/2026.
Johannes | 16.02.2026 | Done | 4734-113 | 4734.113 | 2567110028 |  | T46 |  | 10.179.46.1 | mar5 | v7m | 6.10.0 |  |  | 2025.2.1 | OK | FALSE | switch config updated to v7 on 26/02/2026.
Johannes | 28.01.2026 | Done | 4734-114 | 4734.114 | 2567110022 |  | T44 |  | 10.179.44.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Johannes | 18.02.2026 | Done | 4734-115 | 4734.115 | 2597110027 |  | T61 |  | 10.179.61.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 |  | FALSE
Johannes | 05.03.2026 | Done | 4734-116 | 4734.116 | 2427110030 |  | T3 |  | 10.179.3.1 | mar5 | v7 | 6.10.0 |  |  | 2025.2.1 |  | FALSE
Johannes | 17.03.2026 | Done | 4734-117 | 4734.117 | 2447110010 |  | T14 |  | 10.179.14.1 | mar5 | v7 | 6.10.0 |  |  | 2025.2.1 |  | FALSE
Johannes | 2026-04-07 | Done | 4734-118 | 4734.118 | 2567110023 |  | T48 |  | 10.179.48.1 | mar5 | v6 | 6.10.0 |  |  | 2025.2.1 |  | FALSE
Bahareh | 2026-04-28 | Done | 4734-119 | 4734.119 | 2567110025 |  | T45 |  | 10.179.45.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE |  | 07.05: Strange MAC addresses and double channels noticed. Suggest other train signal
Bahareh | 2026-05-06 | Done | 4734-120 | 4734.120 | 2567110027 |  | T49 |  | 10.179.49.1 | mar5 | v8 | 6.11.2 |  |  | 2025.2.1 |  | FALSE
Bahareh | 2026-05-08 | Done | 4734-121 | 4734.121 | 2577110019 |  | T50 |  | 10.179.50.1 | mar5 | v8 | 6.11.2 |  |  | 2025.2.1 | OK | FALSE
Bahareh | 2026-05-18 | Done | 4734-190 | 4734.190 | 2577110035 |  | T54 |  | 10.179.54.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE | This train is the replacement of 4734-102
Call of 2 and 3 | [16 empty] | FALSE
Davud | Fri 14.03.25 | Investigate | 4706-101 | 4706.101 | 2457110008 |  | T20 |  | 10.179.20.1 | mar5 | v3 | 6.10.0 |  |  | 2025.2.1 |  | FALSE | Long Distance FV. This is Dosto Neu call off 2 - DEL-OBB-039 is in Austria so limited support. Giovanni Di Maio will check if misconfiguration and OEBB will connect with hostpot 19.3 TRAIN IS IN DU
Davud | Fri 04.04.25 | In Progress | 4706-102 | 4706.102 | 2457110015 |  | T15 |  | 10.179.15.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE | 2026-07-09: 18/18 SW fv6-v8-190 (coupler hash-comment fix); AP fw 6.10.0->6.11.2 + config pending; portal 2025Q4 OK
Davud/Giovanni | Mi 14.05.25 | Investigate | 4706-103 | 4706.103 | 2457110011 |  | T17 |  | 10.179.17.1 | mar5 | v6 | 6.10.0 | NOK |  | 2025.2.1 |  | FALSE | CCU migrated to mar5 and switch config updated to v6 on 12/02/2026. More Analyss from Stadler needed (RCU und Sec‑Gateway) . 17/3 Request to check/advise monitors in WAGON F
|  | To Do | TrainNumber 4 | [13 empty] | FALSE
|  | To Do | TrainNumber 5 | [13 empty] | FALSE
|  | To Do | TrainNumber 6 | [13 empty] | FALSE
|  | To Do | TrainNumber 7 | [13 empty] | FALSE
|  | To Do | TrainNumber 8 | [13 empty] | FALSE
|  | To Do | TrainNumber 9 | [13 empty] | FALSE
|  | To Do | TrainNumber 10 | [13 empty] | FALSE
|  | To Do | TrainNumber 11 | [13 empty] | FALSE
|  | To Do | TrainNumber 12 | [13 empty] | FALSE
|  | To Do | TrainNumber 13 | [13 empty] | FALSE
|  | To Do | TrainNumber 14 | [13 empty] | FALSE
Bahareh | 2026-05-22 | DONE | 4734-122 | 4734.122 | 2577110030 |  | T53 |  | 10.179.53.1 | mar5 | v8 | 6.10.0 |  |  | 2025.2.1 |  | FALSE | More regional trains NV. This is Dosto Neu call off 3 - DEL-OBB-039
Bahareh | 2026-06-01 | DONE | 4734-123 | 4734.123 | 2427110028 |  | T67 |  | 10.179.67.1 | mar5 | v8 | 6.11.2 |  |  | 2025.2.1 |  | FALSE
Bahareh | 15.06.2026 | DONE | 4734-124 | 4734.124 | 2577110031 |  | T51 |  | 10.179.51.1 | mar5 | v8 | 6.11.2 |  |  | 2025.2.1 | OK | FALSE
Bahareh | 30.06.2026 | DONE | 4734-125 | 4734.125 | [5 empty] | mar5 | v8 | 6.11.2 |  |  |  |  | FALSE
|  | To Do | TrainNumber 19 | [13 empty] | FALSE
|  | To Do | TrainNumber 20 | [13 empty] | FALSE
|  | To Do | TrainNumber 21 | [13 empty] | FALSE
|  | To Do | TrainNumber 22 | [13 empty] | FALSE
|  | To Do | TrainNumber 23 | [13 empty] | FALSE
|  | To Do | TrainNumber 24 | [13 empty] | FALSE
|  | To Do | TrainNumber 25 | [13 empty] | FALSE
|  | To Do | TrainNumber 26 | [13 empty] | FALSE
|  | To Do | TrainNumber 27 | [13 empty] | FALSE
|  | To Do | TrainNumber 28 | [13 empty] | FALSE
|  | To Do | TrainNumber 29 | [13 empty] | FALSE
|  | To Do | TrainNumber 30 | [13 empty] | FALSE
|  | To Do | TrainNumber 31 | [13 empty] | FALSE
|  | To Do | TrainNumber 32 | [13 empty] | FALSE
|  | To Do | TrainNumber 33 | [13 empty] | FALSE
|  | To Do | TrainNumber 34 | [13 empty] | FALSE
|  | To Do | TrainNumber 35 | [13 empty] | FALSE
Johannes | Mi 03.02.2025 | Done | 4705-101 | 4705.101 | 2547110055 |  | T42 |  | 10.179.42.1 | mar5 | v6 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE | This is City Airport trains - 3 trains, 5 part, DEL-OBB-039
Johannes | 05.03.2026 | Done | 4705-102 | 4705.102 | 2547110047 |  | T43 |  | 10.179.43.1 | mar5 | v7 | 6.10.0 |  |  | 2025.2.1 |  | FALSE
Johannes | 07.04.2026 | Done | 4705-103 | 4705.103 | 2547110065 |  | T41 |  | 10.179.41.1 | mar5 | v6 | 6.10.0 |  |  | 2025.2.1 | OK | FALSE
Call off 5 |  | To Do | [14 empty] | FALSE | This will be call off 5 - 47 trains
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
|  | To Do | [14 empty] | FALSE
Punchlist
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Suggest additional field: MAR 3/5
Note on K6: Source: fleet-status.md / live CCU verification, 2026-07-09. Cell had been auto-converted to date 2003-03-01 by Excel; restored literal 'mar3'.
Note on J8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: this was listed as 10.179.14.1 which is 4734 117
Note on H22: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T15'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on S22: Source: fleet-status.md / live CCU verification, 2026-07-09. Replaces stale 'only 17 SW reachable' note.
Note on E27: Source: fleet-status.md / live CCU verification, 2026-07-09. Fzg-ID cell hygiene: was '4736-002'.
Note on H27: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T02'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on L32: Source: fleet-status.md / live CCU verification, 2026-07-09. 12/12 switches nv4-*-v8-009 since 2026-06-17 (Stadler A1 swap + commission). Was v5.
Note on Q32: Source: fleet-status.md / live CCU verification, 2026-07-09. Portal NDE-2025Q4-12.3.6 verified via https://<ccu>/version.txt sweep 2026-07-09.
Note on E33: Source: fleet-status.md / live CCU verification, 2026-07-09. Fzg-ID cell hygiene: was '4734.11'.
Note on M34: Source: fleet-status.md / live CCU verification, 2026-07-09. 15/15 visible APs at 6.11.2-0 since 2026-05-22 (Gate 4 run). Was 6.10.0.
Note on Q34: Source: fleet-status.md / live CCU verification, 2026-07-09. Portal updated 2023Q4->NDE-2025Q4-12.3.6 on 2026-07-09.
Note on Q35: Source: fleet-status.md / live CCU verification, 2026-07-09. Portal updated 2023Q4->NDE-2025Q4-12.3.6 on 2026-07-09.
Note on Q36: Source: fleet-status.md / live CCU verification, 2026-07-09. Portal updated 2023Q4->NDE-2025Q4-12.3.6 on 2026-07-09.
Note on H38: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T115'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on H39: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T116'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on H40: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T117'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on H41: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T118'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on H42: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T119'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on E43: Source: fleet-status.md / live CCU verification, 2026-07-09. Fzg-ID cell hygiene: was '4734.12'.
Note on H43: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T120'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on H44: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T121'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on Q44: Source: fleet-status.md / live CCU verification, 2026-07-09. Portal updated 2023Q4->NDE-2025Q4-12.3.6 on 2026-07-09.
Note on E45: Source: fleet-status.md / live CCU verification, 2026-07-09. Filled to match column convention (vehicle number).
Note on H45: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T90'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on M45: Source: fleet-status.md / live CCU verification, 2026-07-09. AP fw push (Gate 4) never approved/executed — APs still 6.10.0. Sheet previously claimed 6.11.2.
Note on Q45: Source: fleet-status.md / live CCU verification, 2026-07-09. Portal updated 2023Q4->NDE-2025Q4-12.3.6 on 2026-07-09.
Note on E47: Source: fleet-status.md / live CCU verification, 2026-07-09. Filled to match column convention (vehicle number).
Note on C48: Source: fleet-status.md / live CCU verification, 2026-07-09. Was 'Investigate' — commissioning actively in progress.
Note on E48: Source: fleet-status.md / live CCU verification, 2026-07-09. Filled to match column convention (vehicle number).
Note on H48: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T21'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on L48: Source: fleet-status.md / live CCU verification, 2026-07-09. 18/18 switches on fv6-v8-190 verified 2026-07-09 (coupler template #-comment bug fixed).
Note on Q48: Source: fleet-status.md / live CCU verification, 2026-07-09. Portal NDE-2025Q4-12.3.6 verified 2026-07-09.
Note on S48: Source: fleet-status.md / live CCU verification, 2026-07-09. Replaces stale 'Monitors not reachable' note.
Note on E49: Source: fleet-status.md / live CCU verification, 2026-07-09. Filled to match column convention (vehicle number).
Note on E61: Source: fleet-status.md / live CCU verification, 2026-07-09. Filled to match column convention (vehicle number).
Note on H61: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T122'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on M61: Source: fleet-status.md / live CCU verification, 2026-07-09. Gate 4 (AP fw push) never approved/executed per fleet-status 2026-06-10 — APs still 6.10.0. Was 6.11.2.
Note on D62: Source: fleet-status.md / live CCU verification, 2026-07-09. Train Number format standardised (was '4734 123').
Note on E62: Source: fleet-status.md / live CCU verification, 2026-07-09. Filled to match column convention (vehicle number).
Note on H62: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T123'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on D63: Source: fleet-status.md / live CCU verification, 2026-07-09. Train Number format standardised (was '4734 124').
Note on E63: Source: fleet-status.md / live CCU verification, 2026-07-09. Filled to match column convention (vehicle number).
Note on H63: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T124'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on D64: Source: fleet-status.md / live CCU verification, 2026-07-09. Train Number format standardised (was '4734 125').
Note on E64: Source: fleet-status.md / live CCU verification, 2026-07-09. Filled to match column convention (vehicle number).
Note on D82: Source: fleet-status.md / live CCU verification, 2026-07-09. Train Number format standardised (was '4705 101').
Note on E82: Source: fleet-status.md / live CCU verification, 2026-07-09. Filled to match column convention (vehicle number).
Note on H82: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T101'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on Q82: Source: fleet-status.md / live CCU verification, 2026-07-09. Portal NDE-2025Q4-12.3.6 verified via https://<ccu>/version.txt sweep 2026-07-09.
Note on D83: Source: fleet-status.md / live CCU verification, 2026-07-09. Train Number format standardised (was '4705 102').
Note on E83: Source: fleet-status.md / live CCU verification, 2026-07-09. Filled to match column convention (vehicle number).
Note on H83: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T102'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on D84: Source: fleet-status.md / live CCU verification, 2026-07-09. Train Number format standardised (was '4705 103').
Note on E84: Source: fleet-status.md / live CCU verification, 2026-07-09. Filled to match column convention (vehicle number).
Note on H84: Source: fleet-status.md / live CCU verification, 2026-07-09. NC ID = box-id (CCU hostname box1-t<N> = IP 3rd octet), matching rows 4-24 convention. Was 'T103'. box1-t50/t54/t15 confirmed live via hostname 2026-07-09.
Note on J84: Source: fleet-status.md / live CCU verification, 2026-07-09. Was 10.179.42.1 = duplicate of 4705-101. Correct CCU = box1-t41, validated live 2026-07-07.
Note on Q84: Source: fleet-status.md / live CCU verification, 2026-07-09. Portal NDE-2025Q4-12.3.6 verified via https://<ccu>/version.txt sweep 2026-07-09.