## Issues
ID | Trainset | Consist | Switch / Link | Port(s) | Fault Type | Observed (LLDP/Port state) | Expected (per IP-allocation plan) | Required Action | Status | Date Found | Date Resolved | Stadler Ref / Ticket | Verified By | Notes
1 | 4734-101 | 4-car | E2 ↔ B1 | E2.e0-0 ↔ B1.e0-1 | wrong neighbour | E2.e0-0 reaches B1; B1.e0-1 reaches E2 | E2.e0-0 ↔ E3 (intra-coach); E↔B inter-coach is E1.e0-0 ↔ B1.e0-1 | Re-patch E-coach end so E2.e0-0 lands on E3, and inter-coach E↔B trunk lands on E1.e0-0 ↔ B1.e0-1. | OPEN | 2026-05-06 |  |  | Nomad Digital | Found via lldp_topology_check.py
2 | 4736-108 | 6-car | C3 | e0-0 / e0-1 | cable swap | C3.e0-0 → C2; C3.e0-1 → A2 | C3.e0-0 ↔ A2; C3.e0-1 ↔ C2 | Swap the two trunk cables on C3. After swap, 'show lldp neighbours' on C3 should show e0-0=A2, e0-1=C2. | OPEN | 2026-05-04 |  |  | Nomad Digital | See Stadler_4736-108_Cabling_Fault_Report_v1.0.docx. 2026-05-19: Confirmed active — C3 trunk swap causing STP topology churn. Switches renew DHCP every 2min but IPs constantly shift; SSH TCP SYN sent by CCU but no reply. tcpdump confirms L2 path OK (ARP works) but STP instability prevents stable management access.
3 | 4736-108 | 6-car | D1 ↔ E2 | D1.e0-1 / E2.e0-1 | missing trunk | No LLDP peer either end; both switches reachable on management VLAN | Inter-coach trunk D1.e0-1 ↔ E2.e0-1 | Locate and reconnect inter-coach trunk cable between D1 e0-1 and E2 e0-1. Install replacement if absent. | OPEN | 2026-05-04 |  |  | Nomad Digital | See Stadler_4736-108_Cabling_Fault_Report_v1.0.docx. 2026-05-19: Confirmed active — missing D1↔E2 trunk means coaches D/E are isolated from CCU. Only 5-6 of 18 switches visible at any time.
4 | 4736-109 | 6-car | B3 | e0-4 (AP trunk) | AP not connected | Port admin-enabled, link DOWN, PoE drawing 0 W, no traffic ever | AP physically connected to B3 e0-4 with link UP at 1G full-duplex | Verify whether an AP is physically installed at B3 position. If yes, connect the patch cable to B3 e0-4. | OPEN | 2026-05-04 |  |  | Nomad Digital | See Stadler_4736-109_L2_Health_Check_Report_v1.0.docx
5 | 4736-104 | 6-car | D3 | e1-2 (AP trunk) | faulty SFP/cable | PoE active (~2.5W class-3, device powered) but Ethernet data link never negotiates. Line DOWN, Speed/Duplex stuck Auto/Auto, no MAC learned, all error counters zero. | AP D4 connected to D3 e1-2 with link UP at 1G full-duplex. | 1. Replace patch cable between AP D4 and switch D3 e1-2 (data pairs likely damaged, power pairs intact). 2. If no improvement, swap AP with known-good unit. 3. If still failing, investigate switch-side of D3 e1-2. | OPEN | 2026-05-09 |  |  | Nomad Digital | Confirmed via PoE cycle test on 2026-05-09 (box1-t10, 10.179.10.1). PoE flowing 2.5W class-3 but PHY never negotiates. 23/24 APs visible on 4736-104.
6 | 4734-113 | 6-car(?) | Unknown - 3 switches absent | Unknown | missing trunk | 15 of 18 switches visible in DHCP lease table; 3 switches absent from management VLAN sweep (fping 10.179.42.128-255) | All 18 switches reachable on management VLAN | Identify which 3 cars' switch positions are missing; inspect cable/power at those switch locations. Run LLDP topology check once all switches are reachable. | OPEN | 2026-05-19 |  |  | Nomad Digital | Detected 2026-05-19 via CCU 10.179.42.1 DHCP lease scan. Only 15 leases with VDS OUI a0:59:3a. May indicate 3 switches without power or with cable fault at inter-coach trunk or management port.
7 | 4734-109 | 4-car | B1 / B3 - ZFR access port | B1 e1-11 / B3 e1-11 | AP not connected | Both ZFR access ports (B1 e1-11, B3 e1-11) admin-enabled but link DOWN; no ZFR device responding | B1 e1-11 and B3 e1-11 UP at 1G with ZFR device connected (VLAN 2 access port) | Verify ZFR devices are physically installed and powered at B1 and B3 positions on Fzg 9. Check patch cable from switch port to ZFR unit. | OPEN | 2026-05-19 |  |  | Nomad Digital | Detected 2026-05-19 via CCU 10.179.38.1. show interface B1.e1-11 and B3.e1-11: admin enabled, line protocol down. Switch config v5. FW: ARP at 172.19.132.129 (Westermo default .129 = uncommissioned).
8 | 4734-112 | 5-car | C3 - all 4x10G ports UP | C3 e0-0/e0-1/e0-2/e0-3 | other | C3 switch has 4x10G ports all UP simultaneously - unusual for a non-end-junction switch in a 5-car consist; expected topology only requires 2 inter-coach trunks | C3 should have 2 active inter-coach trunks (e0-0 and e0-1); e0-2/e0-3 role unclear without schema for 4734-112 | Run LLDP topology check on C3 (CCU 10.179.41.1) to identify all 4 peer switch identities. Cross-reference against 4734-112 IP-allocation schema PDF to confirm if e0-2/e0-3 carry a valid purpose or are anomalous. | OPEN | 2026-05-19 |  |  | Nomad Digital | Detected 2026-05-19. Train is 5-car (A,B,C,E,F cars - 15 switches, 20 APs per DHCP). vlan7 was misconfigured (172.19.243.130 stale); fixed to 172.19.134.2/17 and persisted via chroot on 2026-05-19. Switch config v3. C3 anomaly needs schema verification.
Note on A1: Sequential ID. Don't reuse retired IDs.
Note on D1: Use generic switch IDs like A1, D2, E3, B1. For inter-coach links use 'X ↔ Y' (e.g. 'D1 ↔ E2').
Note on E1: Port labels like e0-0, e0-1, e1-8, etc. For trunk pairs: 'X.e0-0 / Y.e0-1'.
Note on F1: Pick from drop-down. Definitions: - cable swap: both cables present, plugged into wrong ports on the same switch. - wrong neighbour: cable goes to the wrong far-end switch. - wrong far-end port: correct switch, wrong port number. - missing trunk: no LLDP either end, cable absent or unplugged. - AP not connected: AP trunk admin-enabled, no link / no PoE draw. - faulty SFP/cable: link UP but error counters non-zero.
Note on J1: OPEN: Stadler action pending. IN PROGRESS: Stadler working on it. RESOLVED: re-verified clean by Nomad. WONTFIX: accepted as-is (e.g. AP not installed by design).

## Dashboard
DOSTO Cable Issues Tracker — Dashboard
Snapshot of open vs. resolved cabling issues across the DOSTO fleet.
Status | Count | Open by Trainset | Open
OPEN |  | 4734-101
IN PROGRESS |  | 4736-108
RESOLVED |  | 4736-109
WONTFIX
TOTAL
|  | Open by Fault Type | Open
cable swap
wrong neighbour
wrong far-end port
missing trunk
AP not connected
faulty SFP/cable
other
How to use this tracker
1. Add new findings as rows on the Issues sheet (next blank row in the table).
2. Use generic switch IDs only (A1…F3 / G1…G3) — no IPs, no MACs, no live hostnames.
3. Fault Type, Status, and Consist have drop-downs — pick from the list.
4. When Stadler fixes an issue: re-run lldp_topology_check.py, then set Status = RESOLVED and fill Date Resolved.
5. Counts on this dashboard refresh automatically.

## Fault Types
Fault Type Reference
Fault Type | Definition | How we detect it | Stadler vs Nomad
cable swap | Both inter-switch trunk cables present, but plugged into wrong ports on the same switch (e0-0 and e0-1 transposed). | lldp_topology_check.py reports two MISMATCHes on the same switch where the live peers are each other's expected peer. | Stadler — re-patch.
wrong neighbour | Cable goes to the wrong far-end switch (e.g. cable that should reach E1 is plugged into E2 instead). | lldp_topology_check.py: live peer ≠ expected peer, and the live peer is a different switch in the same coach group. | Stadler — re-patch.
wrong far-end port | Cable lands on the correct far-end switch, but on the wrong port number. | Inspect both ends; expected port shows NO NEIGHBOUR, an unexpected port shows the link. | Stadler — re-patch.
missing trunk | Inter-coach trunk has no LLDP either end. Cable absent, unplugged, or routed into a dead port. | Both expected endpoints show NO NEIGHBOUR on the affected port. Both switches reachable on management VLAN. | Stadler — locate / install.
AP not connected | AP trunk port admin-enabled, link DOWN, PoE drawing 0 W, no traffic ever. | show interface summary: DOWN. show interface details: 0 RX/TX bytes. PoE: 0 W draw. | Stadler — install AP or patch cable.
faulty SFP/cable | Link UP but per-port error counters are non-zero (RX CRC, carrier-false, etc.) above noise level. | show interface <port> details: RX crc errors, carrier false, or pause frames > 0 sustained. | Stadler — replace SFP or cable.
other | Anything that doesn't fit the categories above. | Document fully in the Notes column on the Issues sheet. | Decide per case.
Note: Template / OBN-config issues (duplicate hostnames, factory dosto-00000000 switches, missing nv4/nv6 templates) are NOT cable issues. They belong in the OBN troubleshooting log, not in this tracker.