## Changes since v1.0
Changes since v1.0 — 2026-06-20 → 2026-07-01
Delta of currently-open port-down problems, keyed on (Train #, Switch, Port). Most CLEARED entries are trains that were offline / last-known-open on 2026-06-20 and have since come back online healthy. APPEARED = went down after 2026-06-20. Infra ports (trunk/AP) are called out separately as priority.
Category
Change | Port-down entries | Distinct trains | Meaning
CLEARED | 233 | 16 | In v1.0, gone now — device reachable again / alarm closed (mostly recovered offline trains)
APPEARED | 56 | 18 | New since 2026-06-20 — went down after the last register
STILL DOWN | 157 | 31 | Present in both — persistent, most likely genuine missing devices
Per-train movement
Train # | Cleared | Appeared | Still down | Note
4734-101 |  |  | 59 | NOT recovered — 59 still down; promote from last-known-open to verify-for-real
4706-102 |  | 17 |  | Whole train appeared — 17 devices, likely first online / not yet fitted
4736-114 | 1 | 4 | 13
4734-108 |  | 1 | 11
4736-111 |  | 1 | 9
4736-112 | 82 |  | 10 | Recovered — 82 cleared
4734-109 |  |  | 10
4736-113 | 24 | 5 | 1 | Mostly recovered
4736-104 | 4 | 5 | 1
4734-103 |  |  | 6
4734-119 |  | 4 | 2
4734-114 |  | 1 | 4
4736-119 | 2 | 3 | 1 | New inter-coach trunk down both ends (B2 e0-0 / B3 e0-1) — priority
4734-105 | 5 |  | 3
4734-118 |  |  | 3
4734-111 |  |  | 3
4736-109 | 1 | 1 | 2
4734-121 |  | 2 | 1
4736-118 | 3 | 2 | 1
4736-108 |  |  | 2
4736-103 |  |  | 2
4734-113 |  |  | 2
4736-117 |  | 2
4736-105 | 22 | 2
4736-101 |  | 2
4734-110 |  |  | 2
4734-116 |  | 1 | 1
4736-107 |  | 2
4736-116 | 5 |  | 1
4734-112 |  |  | 1
4736-102 |  |  | 1
4734-190 | 54 |  | 1 | Recovered — 54 of 55 cleared (was the v1.0 last-known-open cluster)
4734-117 |  |  | 1
4736-106 | 1 |  | 1
4736-115 | 1 |  | 1
4734-120 |  |  | 1
4736-120 | 10 | 1
6025 | 1
6015 | 17
Priority — new infrastructure faults (trunk / AP) since 2026-06-20
Train # | Switch | Port | Category | Device | Open since
4736-119 | B2 | e0-0 | Inter-coach trunk | Switch B3 | 2026-06-30 06:56Z
4736-119 | B3 | e0-1 | Inter-coach trunk | Switch B2 | 2026-06-29 13:51Z
4736-104 | D3 | e1-2 | Access point | AP D4 | 2026-06-30 09:56Z
4736-105 | F2 | e0-4 | Access point | AP F2 | 2026-06-30 10:43Z
4736-114 | A3 | e1-2 | Access point | AP A4 | 2026-07-01 06:02Z

## 6-Teiler (nv6)
DOSTO 6-car (nv6) — Stadler Devices Not Found Register
Currently-OPEN Zabbix port-down problems on template-enabled ports (same source as the NMS dashboard — open problems, not raw event history). Placeholder 7.7.7.7 alarms excluded. Grey = expected-down; amber = missing end-device.
Generated 2026-07-01. 93 open port-down problems across 20 trains — counts match the NMS open-problems view. 'Not found' may be a genuine fault OR a device not yet fitted; Stadler to verify. Offline trains show last-known open problems (re-verify live when next online).
Train # | Train (Zabbix) | Reachability | Switch | Port | Category | Device (OBN template) | Open since | Classification | Verification
4706-102 | 50_6015 | OFFLINE | A1 | e2-2 | Display (Bildschirm) | Bildschirm A1 | 2026-06-24 05:46Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | A1 | e2-3 | Display (Bildschirm) | Bildschirm A3 | 2026-06-24 05:46Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | A2 | e2-3 | Display (Bildschirm) | Bildschirm A4 | 2026-06-24 05:46Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | A3 | e1-14 | Side/front display | Frontanzeige A | 2026-06-24 05:46Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | B2 | e2-3 | Display (Bildschirm) | Bildschirm B4 | 2026-06-22 14:22Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | C1 | e2-4 | Display (Bildschirm) | Bildschirm C | 2026-06-23 05:29Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | C2 | e2-3 | Display (Bildschirm) | Bildschirm C4 | 2026-06-23 05:29Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | D1 | e2-1 | Display (Bildschirm) | Bildschirm D5 | 2026-06-24 05:46Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | D1 | e2-4 | Display (Bildschirm) | Bildschirm D | 2026-06-24 05:46Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | E1 | e1-5 | AFZ | AFZ E1 | 2026-06-24 05:46Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | E2 | e1-7 | AFZ | AFZ E6 | 2026-06-24 05:45Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | E3 | e1-10 | Intercom (Sprechstelle) | Sprechstelle PRM WC | 2026-06-24 05:45Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-24 05:45Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | F1 | e2-4 | Display (Bildschirm) | Bildschirm F | 2026-06-24 05:45Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | F2 | e1-9 | Intercom (Sprechstelle) | Sprechstelle F1R | 2026-06-24 05:46Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | F2 | e2-1 | Display (Bildschirm) | Bildschirm F6 | 2026-06-24 05:46Z | MISSING device | re-verify when online
4706-102 | 50_6015 | OFFLINE | F2 | e2-3 | Display (Bildschirm) | Bildschirm F | 2026-06-24 05:46Z | MISSING device | re-verify when online
4736-101 | 50_6007 | online | E1 | e1-10 | Intercom (Sprechstelle) | Sprechstelle PRM E1 | 2026-06-25 04:45Z | MISSING device | re-verify live
4736-101 | 50_6007 | online | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-25 09:24Z | MISSING device | re-verify live
4736-102 | 50_6047 | online | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-25 04:49Z | MISSING device | re-verify live
4736-103 | 50_6011 | OFFLINE | C2 | e1-5 | AFZ | AFZ C3 | 2026-06-18 11:40Z | MISSING device | re-verify when online
4736-103 | 50_6011 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-18 11:39Z | MISSING device | re-verify when online
4736-104 | 50_6010 | OFFLINE | A2 | e1-7 | NVR | NVR A | 2026-06-30 09:57Z | MISSING device | re-verify when online
4736-104 | 50_6010 | OFFLINE | B1 | e1-8 | Intercom (Sprechstelle) | Sprechstelle B1 | 2026-06-30 09:57Z | MISSING device | re-verify when online
4736-104 | 50_6010 | OFFLINE | D2 | e1-0 | Camera | Interior Camera D8 | 2026-06-30 09:56Z | MISSING device | re-verify when online
4736-104 | 50_6010 | OFFLINE | D3 | e1-2 | Access point | AP D4 | 2026-06-30 09:56Z | MISSING device | re-verify when online
4736-104 | 50_6010 | OFFLINE | E2 | e1-7 | AFZ | AFZ E6 | 2026-06-30 09:57Z | MISSING device | re-verify when online
4736-104 | 50_6010 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-30 05:44Z | MISSING device | re-verify when online
4736-105 | 50_6001 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-30 10:43Z | MISSING device | re-verify when online
4736-105 | 50_6001 | OFFLINE | F2 | e0-4 | Access point | AP F2 | 2026-06-30 10:43Z | MISSING device | re-verify when online
4736-106 | 50_6019 | online | E2 | e1-11 | Intercom (Sprechstelle) | Sprechstelle PRM E1R | 2026-07-01 05:42Z | MISSING device | re-verify live
4736-107 | 50_6025 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-22 09:06Z | MISSING device | re-verify when online
4736-107 | 50_6025 | OFFLINE | F3 | e1-1 | Camera | Exterior Camera F2 | 2026-06-22 08:39Z | MISSING device | re-verify when online
4736-108 | 50_6008 | OFFLINE | A1 | e1-8 | Intercom (Sprechstelle) | Sprechstelle A1 | 2026-06-25 10:29Z | MISSING device | re-verify when online
4736-108 | 50_6008 | OFFLINE | A3 | e1-14 | Side/front display | Frontanzeige A | 2026-06-25 10:31Z | MISSING device | re-verify when online
4736-109 | 50_6028 | OFFLINE | B1 | e0-4 | Access point | AP B1 | 2026-06-29 11:09Z | MISSING device | re-verify when online
4736-109 | 50_6028 | OFFLINE | B2 | e0-4 | Access point | AP B2 | 2026-06-29 11:11Z | MISSING device | re-verify when online
4736-109 | 50_6028 | OFFLINE | E2 | e2-2 | Display (Bildschirm) | Bildschirm E2 | 2026-07-01 00:27Z | MISSING device | re-verify when online
4736-111 | 50_6024 | online | B1 | e2-0 | Display (Bildschirm) | Bildschirm B7 | 2026-06-24 12:08Z | MISSING device | re-verify live
4736-111 | 50_6024 | online | B3 | e1-14 | Side/front display | Frontanzeige B | 2026-07-01 06:00Z | MISSING device | re-verify live
4736-111 | 50_6024 | online | E1 | e2-3 | Display (Bildschirm) | Bildschirm E3 | 2026-07-01 05:58Z | MISSING device | re-verify live
4736-111 | 50_6024 | online | E1 | e2-4 | Display (Bildschirm) | Bildschirm E | 2026-07-01 05:58Z | MISSING device | re-verify live
4736-111 | 50_6024 | online | E3 | e1-9 | Intercom (Sprechstelle) | Sprechstelle E2R | 2026-07-01 05:58Z | MISSING device | re-verify live
4736-111 | 50_6024 | online | E3 | e1-11 | Intercom (Sprechstelle) | Sprechstelle PRM E2R | 2026-07-01 05:58Z | MISSING device | re-verify live
4736-111 | 50_6024 | online | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-07-01 05:58Z | MISSING device | re-verify live
4736-111 | 50_6024 | online | F1 | e2-1 | Display (Bildschirm) | Bildschirm F5 | 2026-06-30 08:42Z | MISSING device | re-verify live
4736-111 | 50_6024 | online | F1 | e2-3 | Display (Bildschirm) | Bildschirm F3 | 2026-06-30 08:42Z | MISSING device | re-verify live
4736-111 | 50_6024 | online | F1 | e2-4 | Display (Bildschirm) | Bildschirm F | 2026-06-30 08:42Z | MISSING device | re-verify live
4736-112 | 50_6040 | online | C2 | e0-4 | Access point | AP C2 | 2026-07-01 05:32Z | MISSING device | re-verify live
4736-112 | 50_6040 | online | C2 | e1-0 | Camera | Interior Camera C8 | 2026-07-01 05:32Z | MISSING device | re-verify live
4736-112 | 50_6040 | online | C2 | e1-1 | Camera | Interior Camera C4 | 2026-07-01 05:32Z | MISSING device | re-verify live
4736-112 | 50_6040 | online | C2 | e1-2 | Camera | Interior Camera C3 | 2026-07-01 05:32Z | MISSING device | re-verify live
4736-112 | 50_6040 | online | C2 | e1-3 | Camera | Interior Camera C6 | 2026-07-01 05:32Z | MISSING device | re-verify live
4736-112 | 50_6040 | online | C2 | e1-4 | Camera | Interior Camera C10 | 2026-07-01 05:32Z | MISSING device | re-verify live
4736-112 | 50_6040 | online | C2 | e1-5 | AFZ | AFZ C3 | 2026-07-01 05:32Z | MISSING device | re-verify live
4736-112 | 50_6040 | online | C2 | e1-6 | AFZ | AFZ C4 | 2026-07-01 05:32Z | MISSING device | re-verify live
4736-112 | 50_6040 | online | F1 | e1-6 | AFZ | AFZ F2 | 2026-07-01 05:34Z | MISSING device | re-verify live
4736-112 | 50_6040 | online | F1 | e1-7 | AFZ | AFZ F5 | 2026-07-01 05:34Z | MISSING device | re-verify live
4736-113 | 50_6022 | online | A1 | e2-3 | Display (Bildschirm) | Bildschirm A3 | 2026-07-01 05:33Z | MISSING device | re-verify live
4736-113 | 50_6022 | online | C1 | e2-4 | Display (Bildschirm) | Bildschirm C | 2026-06-30 05:36Z | MISSING device | re-verify live
4736-113 | 50_6022 | online | C2 | e2-4 | Display (Bildschirm) | Bildschirm C11 | 2026-07-01 05:34Z | MISSING device | re-verify live
4736-113 | 50_6022 | online | D1 | e2-0 | Display (Bildschirm) | Bildschirm D7 | 2026-07-01 05:32Z | MISSING device | re-verify live
4736-113 | 50_6022 | online | D2 | e1-14 | Side/front display | Seitenanzeige D2 | 2026-06-30 10:09Z | MISSING device | re-verify live
4736-113 | 50_6022 | online | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-07-01 05:37Z | MISSING device | re-verify live
4736-114 | 50_6027 | online | A1 | e2-2 | Display (Bildschirm) | Bildschirm A1 | 2026-06-30 13:19Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | A3 | e1-2 | Access point | AP A4 | 2026-07-01 06:02Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | B1 | e2-0 | Display (Bildschirm) | Bildschirm B7 | 2026-06-30 14:12Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | B1 | e2-1 | Display (Bildschirm) | Bildschirm B5 | 2026-06-29 07:55Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | B1 | e2-3 | Display (Bildschirm) | Bildschirm B3 | 2026-06-20 07:43Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | B2 | e2-2 | Display (Bildschirm) | Bildschirm B2 | 2026-07-01 06:03Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | B3 | e1-14 | Side/front display | Frontanzeige B | 2026-06-30 14:00Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | C1 | e2-0 | Display (Bildschirm) | Bildschirm C7 | 2026-06-30 07:43Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | C1 | e2-1 | Display (Bildschirm) | Bildschirm C5 | 2026-07-01 06:07Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | C1 | e2-3 | Display (Bildschirm) | Bildschirm C3 | 2026-07-01 06:07Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | C2 | e2-1 | Display (Bildschirm) | Bildschirm C6 | 2026-06-30 05:47Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | D2 | e2-0 | Display (Bildschirm) | Bildschirm D8 | 2026-06-30 05:47Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | E1 | e2-0 | Display (Bildschirm) | Bildschirm E7 | 2026-06-29 07:56Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | E2 | e2-2 | Display (Bildschirm) | Bildschirm E2 | 2026-06-29 07:56Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-07-01 06:02Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | F1 | e2-3 | Display (Bildschirm) | Bildschirm F3 | 2026-06-30 05:47Z | MISSING device | live-confirmed 2026-07-01
4736-114 | 50_6027 | online | F3 | e1-9 | Intercom (Sprechstelle) | Sprechstelle F2R | 2026-07-01 06:03Z | MISSING device | live-confirmed 2026-07-01
4736-115 | 50_6018 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-30 13:14Z | MISSING device | re-verify when online
4736-116 | 50_6016 | OFFLINE | F1 | e2-4 | Display (Bildschirm) | Bildschirm F | 2026-06-30 06:01Z | MISSING device | re-verify when online
4736-117 | 50_6032 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-30 06:05Z | MISSING device | re-verify when online
4736-117 | 50_6032 | OFFLINE | F1 | e2-4 | Display (Bildschirm) | Bildschirm F | 2026-06-30 06:05Z | MISSING device | re-verify when online
4736-118 | 50_6021 | OFFLINE | B1 | e1-11 | ZFR | ZFR R | 2026-06-29 14:39Z | MISSING device | re-verify when online
4736-118 | 50_6021 | OFFLINE | C1 | e2-0 | Display (Bildschirm) | Bildschirm C7 | 2026-06-30 06:06Z | MISSING device | re-verify when online
4736-118 | 50_6021 | OFFLINE | D1 | e2-4 | Display (Bildschirm) | Bildschirm D | 2026-06-29 14:39Z | MISSING device | re-verify when online
4736-119 | 50_6012 | OFFLINE | B2 | e0-0 | Inter-coach trunk | Switch B3 | 2026-06-30 06:56Z | expected-down | re-verify when online
4736-119 | 50_6012 | OFFLINE | B3 | e0-1 | Inter-coach trunk | Switch B2 | 2026-06-29 13:51Z | expected-down | re-verify when online
4736-119 | 50_6012 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-29 13:51Z | MISSING device | re-verify when online
4736-119 | 50_6012 | OFFLINE | F1 | e1-7 | AFZ | AFZ F5 | 2026-06-29 13:51Z | MISSING device | re-verify when online
4736-120 | 50_6002 | online | C2 | e2-1 | Display (Bildschirm) | Bildschirm C6 | 2026-06-30 08:58Z | MISSING device | re-verify live

## 6-Teiler Summary
Summary — missing devices by train and category
Train # | Missing devices |  | Category | Count
4706-102 | 17 |  | Display (Bildschirm) | 40
4736-114 | 17 |  | Energy meter | 13
4736-111 | 10 |  | AFZ | 9
4736-112 | 10 |  | Intercom (Sprechstelle) | 9
4736-104 | 6 |  | Camera | 7
4736-113 | 6 |  | Access point | 6
4736-109 | 3 |  | Side/front display | 5
4736-118 | 3 |  | NVR | 1
4736-101 | 2 |  | ZFR | 1
4736-103 | 2
4736-105 | 2
4736-107 | 2
4736-108 | 2
4736-117 | 2
4736-119 | 2
4736-102 | 1
4736-106 | 1
4736-115 | 1
4736-116 | 1
4736-120 | 1
Priority entries — infrastructure ports (trunk / AP)
Train # | Switch | Port | Device | Open since
4736-104 | D3 | e1-2 | Access point: AP D4 | 2026-06-30 09:56Z
4736-105 | F2 | e0-4 | Access point: AP F2 | 2026-06-30 10:43Z
4736-109 | B1 | e0-4 | Access point: AP B1 | 2026-06-29 11:09Z
4736-109 | B2 | e0-4 | Access point: AP B2 | 2026-06-29 11:11Z
4736-112 | C2 | e0-4 | Access point: AP C2 | 2026-07-01 05:32Z
4736-114 | A3 | e1-2 | Access point: AP A4 | 2026-07-01 06:02Z
4736-119 | B2 | e0-0 | Inter-coach trunk: Switch B3 | 2026-06-30 06:56Z
4736-119 | B3 | e0-1 | Inter-coach trunk: Switch B2 | 2026-06-29 13:51Z

## 4-Teiler (nv4)
DOSTO 4-car (nv4) — Stadler Devices Not Found Register
Currently-OPEN Zabbix port-down problems on template-enabled ports (same source as the NMS dashboard — open problems, not raw event history). Placeholder 7.7.7.7 alarms excluded. Grey = expected-down; amber = missing end-device.
Generated 2026-07-01. 120 open port-down problems across 17 trains — counts match the NMS open-problems view. 'Not found' may be a genuine fault OR a device not yet fitted; Stadler to verify. Offline trains show last-known open problems (re-verify live when next online).
Train # | Train (Zabbix) | Reachability | Switch | Port | Category | Device (OBN template) | Open since | Classification | Verification
4734-101 | 50_4004 | OFFLINE | A1 | e1-14 | Side/front display | Seitenanzeige A1 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A1 | e1-15 | Side/front display | Seitenanzeige A3 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A1 | e2-0 | Display (Bildschirm) | Bildschirm A7 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A1 | e2-1 | Display (Bildschirm) | Bildschirm A5 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A1 | e2-2 | Display (Bildschirm) | Bildschirm A1 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A1 | e2-3 | Display (Bildschirm) | Bildschirm A3 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A2 | e1-14 | Side/front display | Seitenanzeige A2 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A2 | e1-15 | Side/front display | Seitenanzeige A4 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A2 | e2-0 | Display (Bildschirm) | Bildschirm A8 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A2 | e2-1 | Display (Bildschirm) | Bildschirm A6 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A2 | e2-2 | Display (Bildschirm) | Bildschirm A2 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A2 | e2-3 | Display (Bildschirm) | Bildschirm A4 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A3 | e1-1 | Camera | Exterior Camera A2 | 2026-06-16 06:28Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | A3 | e1-14 | Side/front display | Frontanzeige A | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B1 | e1-8 | Intercom (Sprechstelle) | Sprechstelle B1 | 2026-06-16 06:27Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B1 | e1-14 | Side/front display | Seitenanzeige B1 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B1 | e1-15 | Side/front display | Seitenanzeige B3 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B1 | e2-0 | Display (Bildschirm) | Bildschirm B7 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B1 | e2-1 | Display (Bildschirm) | Bildschirm B5 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B1 | e2-2 | Display (Bildschirm) | Bildschirm B1 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B1 | e2-3 | Display (Bildschirm) | Bildschirm B3 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B2 | e1-14 | Side/front display | Seitenanzeige B2 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B2 | e1-15 | Side/front display | Seitenanzeige B4 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B2 | e2-0 | Display (Bildschirm) | Bildschirm B8 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B2 | e2-1 | Display (Bildschirm) | Bildschirm B6 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B2 | e2-2 | Display (Bildschirm) | Bildschirm B2 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B2 | e2-3 | Display (Bildschirm) | Bildschirm B4 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | B3 | e1-14 | Side/front display | Frontanzeige B | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E1 | e1-14 | Side/front display | Seitenanzeige E1 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E1 | e1-15 | Side/front display | Seitenanzeige E3 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E1 | e2-0 | Display (Bildschirm) | Bildschirm E7 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E1 | e2-1 | Display (Bildschirm) | Bildschirm E5 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E1 | e2-2 | Display (Bildschirm) | Bildschirm E1 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E1 | e2-3 | Display (Bildschirm) | Bildschirm E3 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E1 | e2-4 | Display (Bildschirm) | Bildschirm E | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E2 | e0-1 | Inter-coach trunk | Switch D1 | 2026-06-16 06:28Z | expected-down | re-verify when online
4734-101 | 50_4004 | OFFLINE | E2 | e1-14 | Side/front display | Seitenanzeige E2 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E2 | e1-15 | Side/front display | Seitenanzeige E4 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E2 | e2-0 | Display (Bildschirm) | Bildschirm E8 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E2 | e2-1 | Display (Bildschirm) | Bildschirm E6 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E2 | e2-2 | Display (Bildschirm) | Bildschirm E2 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E2 | e2-3 | Display (Bildschirm) | Bildschirm E4 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E2 | e2-4 | Display (Bildschirm) | Bildschirm E11 | 2026-06-16 13:59Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-16 06:28Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G1 | e0-1 | Inter-coach trunk | Switch E2 | 2026-06-12 12:18Z | expected-down | re-verify when online
4734-101 | 50_4004 | OFFLINE | G1 | e1-14 | Side/front display | Seitenanzeige D1 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G1 | e1-15 | Side/front display | Seitenanzeige D3 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G1 | e2-0 | Display (Bildschirm) | Bildschirm D7 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G1 | e2-1 | Display (Bildschirm) | Bildschirm D5 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G1 | e2-2 | Display (Bildschirm) | Bildschirm D1 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G1 | e2-3 | Display (Bildschirm) | Bildschirm D3 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G1 | e2-4 | Display (Bildschirm) | Bildschirm D | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G2 | e1-14 | Side/front display | Seitenanzeige D2 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G2 | e1-15 | Side/front display | Seitenanzeige D4 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G2 | e2-0 | Display (Bildschirm) | Bildschirm D8 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G2 | e2-1 | Display (Bildschirm) | Bildschirm D6 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G2 | e2-2 | Display (Bildschirm) | Bildschirm D2 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G2 | e2-3 | Display (Bildschirm) | Bildschirm D4 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-101 | 50_4004 | OFFLINE | G2 | e2-4 | Display (Bildschirm) | Bildschirm D11 | 2026-06-16 14:00Z | MISSING device | re-verify when online
4734-103 | 50_4005 | OFFLINE | B2 | e2-0 | Display (Bildschirm) | Bildschirm B8 | 2026-06-15 06:40Z | MISSING device | re-verify when online
4734-103 | 50_4005 | OFFLINE | B2 | e2-1 | Display (Bildschirm) | Bildschirm B6 | 2026-06-15 06:40Z | MISSING device | re-verify when online
4734-103 | 50_4005 | OFFLINE | E1 | e1-10 | Intercom (Sprechstelle) | Sprechstelle PRM E1 | 2026-06-15 06:50Z | MISSING device | re-verify when online
4734-103 | 50_4005 | OFFLINE | E1 | e2-1 | Display (Bildschirm) | Bildschirm E5 | 2026-06-15 06:50Z | MISSING device | re-verify when online
4734-103 | 50_4005 | OFFLINE | E2 | e1-9 | Intercom (Sprechstelle) | Sprechstelle E1R | 2026-06-15 06:53Z | MISSING device | re-verify when online
4734-103 | 50_4005 | OFFLINE | E2 | e2-3 | Display (Bildschirm) | Bildschirm E4 | 2026-06-15 06:53Z | MISSING device | re-verify when online
4734-105 | 50_4030 | online | B1 | e2-1 | Display (Bildschirm) | Bildschirm B5 | 2026-07-01 05:44Z | MISSING device | re-verify live
4734-105 | 50_4030 | online | B2 | e1-5 | AFZ | AFZ B3 | 2026-07-01 05:44Z | MISSING device | re-verify live
4734-105 | 50_4030 | online | E1 | e1-7 | AFZ | AFZ E5 | 2026-06-30 09:12Z | MISSING device | re-verify live
4734-108 | 50_4029 | online | A2 | e1-0 | Camera | Interior Camera A8 | 2026-06-29 06:22Z | MISSING device | re-verify live
4734-108 | 50_4029 | online | A3 | e1-14 | Side/front display | Frontanzeige A | 2026-06-29 11:06Z | MISSING device | re-verify live
4734-108 | 50_4029 | online | B1 | e2-0 | Display (Bildschirm) | Bildschirm B7 | 2026-06-15 15:04Z | MISSING device | re-verify live
4734-108 | 50_4029 | online | B2 | e2-0 | Display (Bildschirm) | Bildschirm B8 | 2026-06-11 09:07Z | MISSING device | re-verify live
4734-108 | 50_4029 | online | E2 | e1-7 | AFZ | AFZ E6 | 2026-06-10 13:13Z | MISSING device | re-verify live
4734-108 | 50_4029 | online | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-11 09:08Z | MISSING device | re-verify live
4734-108 | 50_4029 | online | G1 | e1-7 | AFZ | AFZ D5 | 2026-06-29 06:21Z | MISSING device | re-verify live
4734-108 | 50_4029 | online | G1 | e2-1 | Display (Bildschirm) | Bildschirm D5 | 2026-06-30 11:51Z | MISSING device | re-verify live
4734-108 | 50_4029 | online | G2 | e0-1 | Inter-coach trunk | Switch E1 | 2026-06-29 06:21Z | expected-down | re-verify live
4734-108 | 50_4029 | online | G2 | e1-6 | AFZ | AFZ D4 | 2026-06-29 06:21Z | MISSING device | re-verify live
4734-108 | 50_4029 | online | G2 | e1-8 | Intercom (Sprechstelle) | Sprechstelle D2 | 2026-06-29 06:21Z | MISSING device | re-verify live
4734-108 | 50_4029 | online | G3 | e1-9 | Intercom (Sprechstelle) | Sprechstelle D2R | 2026-06-29 06:21Z | MISSING device | re-verify live
4734-109 | 50_4038 | OFFLINE | A1 | e1-0 | Camera | Interior Camera A7 | 2026-06-17 10:05Z | MISSING device | re-verify when online
4734-109 | 50_4038 | OFFLINE | A1 | e1-1 | Camera | Interior Camera A2 | 2026-06-17 10:05Z | MISSING device | re-verify when online
4734-109 | 50_4038 | OFFLINE | A1 | e2-5 | Audio/ADU | Audio Amp. A1 | 2026-06-17 10:05Z | MISSING device | re-verify when online
4734-109 | 50_4038 | OFFLINE | A2 | e1-6 | AFZ | AFZ A4 | 2026-06-17 06:11Z | MISSING device | re-verify when online
4734-109 | 50_4038 | OFFLINE | E1 | e1-7 | AFZ | AFZ E5 | 2026-06-17 06:12Z | MISSING device | re-verify when online
4734-109 | 50_4038 | OFFLINE | E1 | e2-0 | Display (Bildschirm) | Bildschirm E7 | 2026-06-17 06:12Z | MISSING device | re-verify when online
4734-109 | 50_4038 | OFFLINE | E1 | e2-1 | Display (Bildschirm) | Bildschirm E5 | 2026-06-17 06:12Z | MISSING device | re-verify when online
4734-109 | 50_4038 | OFFLINE | E2 | e1-7 | AFZ | AFZ E6 | 2026-06-17 06:12Z | MISSING device | re-verify when online
4734-109 | 50_4038 | OFFLINE | E2 | e2-1 | Display (Bildschirm) | Bildschirm E6 | 2026-06-17 06:12Z | MISSING device | re-verify when online
4734-109 | 50_4038 | OFFLINE | G1 | e1-7 | AFZ | AFZ D5 | 2026-06-17 06:11Z | MISSING device | re-verify when online
4734-110 | 50_4036 | OFFLINE | E2 | e1-8 | Intercom (Sprechstelle) | Sprechstelle E2 | 2026-06-29 17:06Z | MISSING device | re-verify when online
4734-110 | 50_4036 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-29 17:07Z | MISSING device | re-verify when online
4734-111 | 50_4039 | online | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-07-01 05:52Z | MISSING device | re-verify live
4734-111 | 50_4039 | online | G1 | e2-4 | Display (Bildschirm) | Bildschirm D | 2026-06-30 14:06Z | MISSING device | re-verify live
4734-111 | 50_4039 | online | G2 | e2-4 | Display (Bildschirm) | Bildschirm D11 | 2026-07-01 05:52Z | MISSING device | re-verify live
4734-112 | 50_4037 | online | G1 | e2-0 | Display (Bildschirm) | Bildschirm D7 | 2026-07-01 06:16Z | MISSING device | re-verify live
4734-113 | 50_4046 | OFFLINE | E2 | e2-1 | Display (Bildschirm) | Bildschirm E6 | 2026-06-29 12:14Z | MISSING device | re-verify when online
4734-113 | 50_4046 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-29 12:30Z | MISSING device | re-verify when online
4734-114 | 50_4044 | OFFLINE | A1 | e1-15 | Side/front display | Seitenanzeige A3 | 2026-06-30 11:14Z | MISSING device | re-verify when online
4734-114 | 50_4044 | OFFLINE | E2 | e2-2 | Display (Bildschirm) | Bildschirm E2 | 2026-06-30 08:05Z | MISSING device | re-verify when online
4734-114 | 50_4044 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-30 08:05Z | MISSING device | re-verify when online
4734-114 | 50_4044 | OFFLINE | G1 | e2-3 | Display (Bildschirm) | Bildschirm D3 | 2026-06-30 08:05Z | MISSING device | re-verify when online
4734-114 | 50_4044 | OFFLINE | G2 | e1-8 | Intercom (Sprechstelle) | Sprechstelle D2 | 2026-06-30 08:06Z | MISSING device | re-verify when online
4734-116 | 50_4003 | OFFLINE | B1 | e2-0 | Display (Bildschirm) | Bildschirm B7 | 2026-06-30 10:28Z | MISSING device | re-verify when online
4734-116 | 50_4003 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-25 06:54Z | MISSING device | re-verify when online
4734-117 | 50_4014 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-12 07:32Z | MISSING device | re-verify when online
4734-118 | 50_4048 | OFFLINE | A2 | e1-7 | NVR | NVR A | 2026-06-12 08:54Z | MISSING device | re-verify when online
4734-118 | 50_4048 | OFFLINE | B2 | e1-7 | NVR | NVR B | 2026-06-12 07:38Z | MISSING device | re-verify when online
4734-118 | 50_4048 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-12 08:53Z | MISSING device | re-verify when online
4734-119 | 50_4045 | online | A1 | e1-5 | AFZ | AFZ A1 | 2026-07-01 06:12Z | MISSING device | re-verify live
4734-119 | 50_4045 | online | B1 | e1-5 | AFZ | AFZ B1 | 2026-07-01 06:16Z | MISSING device | re-verify live
4734-119 | 50_4045 | online | B2 | e1-5 | AFZ | AFZ B3 | 2026-07-01 06:16Z | MISSING device | re-verify live
4734-119 | 50_4045 | online | E2 | e1-8 | Intercom (Sprechstelle) | Sprechstelle E2 | 2026-07-01 06:17Z | MISSING device | re-verify live
4734-119 | 50_4045 | online | E2 | e2-1 | Display (Bildschirm) | Bildschirm E6 | 2026-07-01 06:17Z | MISSING device | re-verify live
4734-119 | 50_4045 | online | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-07-01 06:13Z | MISSING device | re-verify live
4734-120 | 50_4049 | OFFLINE | B2 | e1-7 | NVR | NVR B | 2026-06-30 06:22Z | MISSING device | re-verify when online
4734-121 | 50_4050 | online | E2 | e1-5 | AFZ | AFZ E3 | 2026-06-30 05:28Z | MISSING device | re-verify live
4734-121 | 50_4050 | online | E2 | e1-9 | Intercom (Sprechstelle) | Sprechstelle E1R | 2026-06-30 05:28Z | MISSING device | re-verify live
4734-121 | 50_4050 | online | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-30 05:33Z | MISSING device | re-verify live
4734-190 | 50_4054 | OFFLINE | E3 | e2-0 | Energy meter | Energiezaehler E | 2026-06-30 05:23Z | MISSING device | re-verify when online

## 4-Teiler Summary
Summary — missing devices by train and category
Train # | Missing devices |  | Category | Count
4734-101 | 57 |  | Display (Bildschirm) | 55
4734-108 | 11 |  | Side/front display | 20
4734-109 | 10 |  | AFZ | 13
4734-103 | 6 |  | Energy meter | 12
4734-119 | 6 |  | Intercom (Sprechstelle) | 9
4734-114 | 5 |  | Camera | 4
4734-105 | 3 |  | NVR | 3
4734-111 | 3 |  | Audio/ADU | 1
4734-118 | 3
4734-121 | 3
4734-110 | 2
4734-113 | 2
4734-116 | 2
4734-112 | 1
4734-117 | 1
4734-120 | 1
4734-190 | 1
Priority entries — infrastructure ports (trunk / AP)
Train # | Switch | Port | Device | Open since
4734-101 | E2 | e0-1 | Inter-coach trunk: Switch D1 | 2026-06-16 06:28Z
4734-101 | G1 | e0-1 | Inter-coach trunk: Switch E2 | 2026-06-12 12:18Z
4734-108 | G2 | e0-1 | Inter-coach trunk: Switch E1 | 2026-06-29 06:21Z
4734-101 (59) and 4734-190 (55) account for most of the 4-car total. On each, ~54 of these ports went DOWN within a ~1-minute window (101: 2026-06-16 13:59-14:00Z; 190: 2026-06-17 08:49-08:50Z) and the train then went offline. These are last-known-open alarms — pending LIVE re-verification when 101/190 are back online; do not treat as confirmed per-device faults until then.